## Risk Reg
SWANBOURNE PARISH COUNCIL
RISK REGISTER
2022/23
Ref | Type | Risk | Impact | Likelihood | Score | Mitigating actions | Impact | Likelihood | Score | Review and comments
R1 | Financial | Loss of financial assets through fraud or poor accounting records | 3 | 1 | 3 | 1. Two signatories for payment approval 2. Quarterly bank reconcilation presented to PC 3. Annual independent audit 4. Schedule of income & expenditure ratified at each council meeting 5. References and DBS checks concluded before RFO takes up post | 3 | 1 | 3
R2 | Financial | Insuffient reserves to cover unexpected large expenditure | 3 | 2 | 6 | 1. Regular (quarterly) review of expenditure compared to budget 2. Gradual increase in precept and cash reserves 3. Good forward planning and budgeting | 2 | 2 | 4
R3 | Property Reputation | Injury to individuals as a consequence of the Council providing amenities to the public: playing field and equipment | 3 | 2 | 6 | 1. Public liability insurance 2. ROSPA annual inspection of equipment 3. Playing field working group to review and maintain equipment 4. Regular reports to PC by Playing Field working group 5. Equipment maintenance check and inspection records | 3 | 1 | 3
R4 | Legal | Loss of legal documents and/or Council records | 2 | 2 | 4 | 1. Storage and document retention policy 2. Electronic backups 3. Availability of key documents via the website | 2 | 1 | 2
R5 | Property | Damage to physical assets owned by the Council: playing field equipment, benches, bus shelters, noticeboard, street lights | 2 | 2 | 4 | 1. Adequate insurance cover 2. Regular checks and maintenance 3. Maintenance budget and availability of funds 4. Physical verifcation of assets held on asset register | 2 | 1 | 2
R6 | Property | Failure of equipment provided by the Council: defibrillator, garden equipment | 3 | 1 | 3 | 1. Regular inspection and testing of equipment 2. Risk assessments conducted | 2 | 1 | 2
R7 | Legal | Damage to third party property or individuals as a consequence of Council putting on community event | 3 | 2 | 6 | 1. H&S risk assessments conducted 2. Event checklist 3. Insurance cover in place. | 3 | 1 | 3
R8 | Legal | Employer liability | 2 | 1 | 2 | 1. Insurance policy in place | 1 | 1 | 1
R9 | Reputation | Sudden loss of clerk or Council members | 3 | 1 | 3 | 1. Responsibilities are shared to reduce immediate impact 2. Council vacancies are replaced asap to ensure continuity and quorate membership 3. Clerks systems are kept up to date 4. Council are aware of clerk roles and responsibilities | 2 | 1 | 2
R10 | Legal | Non maintenance of Council defibrillator resulting in failure of equipment during emergency situation | 3 | 2 | 6 | 1. Councillor to be responsible for maintenance including battery and sucker check. 2. Ownership, responsibility and location to be made clear and linked to asset register | 3 | 1 | 3

## Matrix
SWANBOURNE PARISH COUNCIL
RISK MANAGEMENT MATRIX
Likelihood
|  | 1 | 2 | 3
Impact | 1 | 1x1 Low | 1x2 Low | 1 x 3 Med
| 2 | 1x2 Low | 2x2 Med | 2x3 High
| 3 | 1x3 Med | 2x3 High | 3x3 High